## v5 Changelog
MML Study Plan v5 Changelog
Date: 2026-05-24
Status: 3 days into v4 (Wk 1 Mon-Wed done). v5 takes effect from Wk 4 onwards.
WHAT CHANGED FROM v4
Change | Description
1. Cut Wk 13 Buffer week | Original buffer week eliminated to fit 10-week window
2. Cut Wk 14 Capstone (NN on MNIST) | Capstone deferred. PyTorch IO already covers NN implementation. Optional post-plan.
3. Compressed Ch 6 Probability from 2 weeks to 1 week (Wk 9) | Tighter reading pace (2 sections/day), fewer exercises (4 highest-value picks), combined implementation days. Loses some depth.
4. Compressed Ch 7 Optimization from 2 weeks to 1 week (Wk 10) | Tighter reading pace, combined Python implementation days. Loses some breadth on LR schedules and edge cases.
5. ADDED Shalev-Shwartz parallel track (NEW) | SSW Ch 1-6 reading starts Wk 4 (after PyTorch ends). 30-45 min/day. Light reading for ML 391L head start.
6. Added SSW columns to Daily Plan | SSW Chapter, SSW Section, SSW Tasks, SSW Time columns appear from Wk 4 onwards
7. Updated GitHub Milestones | Added v0.7-ssw-phase1 tag for SSW summary doc
8. Updated Progress Tracker | Added SSW Linked Ch column. Added SSW Phase 1 row.
WORKLOAD COMPARISON
Period | v4 | v5
Total weeks | 14 | 10
Total study days | 98 | 70
Plan end date | 2026-08-25 | 2026-07-28
Buffer before Fall classes (Aug 25) | 0 days | ~4 weeks (Jul 29-Aug 25)
Wk 1-3 daily load (MML + PT) | 110-150 min/day | 110-150 min/day (UNCHANGED)
Wk 4-8 daily load (MML + SSW) | 50-90 min/day (MML only) | 80-135 min/day (MML 50-90 + SSW 30-45)
Wk 9-10 daily load (compressed MML + SSW) | 50-90 min/day | 80-110 min/day (compressed MML 70-80 + SSW 30)
POST-PLAN RECOMMENDATIONS
1. Use Jul 29 - Aug 25 (4 weeks) for: PyTorch deep practice on personal project OR start reading Krähenbühl DL course materials OR rest before semester starts
2. Continue SSW Ch 7+ (Linear Predictors, Boosting) lightly during Fall 2026 semester. 1-2 hrs/week.
3. Re-read SSW Ch 1-6 + read Ch 7-10 during Dec 2026/Jan 2027 break before ML 391L starts.
4. Buy Blitzstein for probability prep (recommended by ML 391L prereqs) and start light reading during Fall semester.
DATE SHIFT (v5.1, applied 2026-05-24)
Days 1-3 (May 18-20) DONE. Days 4-70 shifted +2 days.
Old Day 4 = Sat May 23, New Day 4 = Mon May 25, 2026
Old plan end = Jul 28, New plan end = Jul 30, 2026
Buffer before Fall classes (Aug 25): ~3.5 weeks (was 4 weeks)

## Source Map
MML Topic | MML Section | GT ILA Coverage | GT ILA Sections | Supplement from MML? | Week
Systems of Linear Equations | 2.1, 2.3 | FULLY covered by GT ILA | GT Ch 1: Systems, Row Reduction, Parametric Form | No | Wk 1
Matrices, Multiplication, Inverse | 2.2, 2.3 | FULLY covered by GT ILA | GT Ch 3: Matrix Mult, Inverses, Invertible Matrix Thm | No | Wk 1
Vector Spaces, Subspaces | 2.4 | PARTIALLY covered | GT Ch 2: Subspaces | Yes: MML 2.4 group/axiom pages (20 min) | Wk 1
Linear Independence | 2.5 | FULLY covered by GT ILA | GT Ch 2: Linear Independence | No | Wk 1
Basis, Rank, Image, Kernel | 2.6 | FULLY covered by GT ILA | GT Ch 2: Basis & Dimension, Coordinate Systems, Rank Thm | No | Wk 1
Linear Mappings | 2.7 | FULLY covered by GT ILA | GT Ch 3: Matrix Transformations, Linear Transformations, 1-1/Onto | No | Wk 1
Affine Spaces | 2.8 | NOT covered | N/A | Yes: MML 2.8 full section (30-45 min) | Wk 1
Norms, Inner Products, Angles | 3.1-3.3 | FULLY covered by GT ILA | GT Ch 6: Dot Products and Orthogonality | No | Wk 4
Orthogonal Projections | 3.4 | FULLY covered by GT ILA | GT Ch 6: Orthogonal Projection, Orthogonal Sets | No | Wk 4
Least Squares (bonus) | 3.4+ | Covered by GT ILA | GT Ch 6: Method of Least Squares | No | Wk 4
Determinants | 4.1 | FULLY covered by GT ILA | GT Ch 4: Definition, Cofactor Expansions, Volumes | No | Wk 5
Eigenvalues & Eigenvectors | 4.2 | FULLY covered by GT ILA | GT Ch 5: Eigenvalues, Characteristic Polynomial, Diagonalization | No | Wk 5
Diagonalization | 4.3 | FULLY covered by GT ILA | GT Ch 5: Similarity, Diagonalization | No | Wk 5
SVD | 4.4 | NOT covered | N/A | Yes: MML 4.4 full section (critical) | Wk 5
Matrix Approximation / PCA | 4.5 | NOT covered | N/A | Yes: MML 4.5 full section (critical) | Wk 5
Vector Calculus (Ch 5) | 5.1-5.6 | NOT covered | N/A | MML only | Wk 7-8
Probability (Ch 6) | 6.1-6.6 | NOT covered | N/A | MML only | Wk 9-10
Optimization (Ch 7) | 7.1-7.4 | NOT covered | N/A | MML only | Wk 11-12
SHALEV-SHWARTZ SUPPLEMENT (NEW v5)
SSW Topic | SSW Chapter | Reading Depth | Purpose | Week
Intro & Notation | Ch 1 | Full read | Set up SSW framing and notation | Wk 4
A Gentle Start (PAC intuition) | Ch 2 | Full read + exercises | PAC framework foundation | Wk 5-6
Formal Learning Model (PAC) | Ch 3 | Full read + exercises | Formal PAC definitions | Wk 6-7
Uniform Convergence | Ch 4 | Skim, theorem statements only | High-level connection to ERM | Wk 7-8
Bias-Complexity (NFL) | Ch 5 | Full read | No Free Lunch theorem, error decomposition | Wk 8
VC Dimension | Ch 6 | Skim definitions and examples | VC intuition only; save proofs for ML 391L Spring 2027 | Wk 9

## Daily Plan
Week | Chapter | Date | Day | Source | Type | Sections | Focus Topic | Tasks & Deliverables | GitHub Deliverable | Time | Status | PT Chapter | PT Topic | PT Tasks | PT Time | SSW Chapter | SSW Section | SSW Tasks | SSW Time
1 | Ch 2 | 2026-05-18 | Monday | GT ILA | Read | GT Ch 1 (all 3 sections) | Systems of Linear Equations | Read all of GT ILA Ch 1: Systems of Linear Equations, Row Reduction, Parametric Form. Play with every interactive demo. Do embedded exercises. | Init repo: README.md, .gitignore, requirements.txt, ch02/ | 50
1 | Ch 2 | 2026-05-19 | Tuesday | GT ILA | Read | GT Ch 1 (finish) + start Ch 2 | Row Reduction + Vectors & Spans | Finish Ch 1 exercises if any remain. Start GT Ch 2: Vectors, Vector Equations and Spans, Matrix Equations. Focus on geometric interpretation. |  | 50 |  | Ch 00 | Tensors: Creation & Operations | Tensor creation (torch.tensor, zeros, ones, rand, arange). Dtypes, shapes, devices. Basic operations: add, mul, matmul. Reshaping: view, reshape, permute, squeeze, unsqueeze. | 60
1 | Ch 2 | 2026-05-20 | Wednesday | GT ILA | Read | GT Ch 2 (sections 1-5) | Solution Sets, Linear Independence, Subspaces | Continue GT Ch 2: Solution Sets, Linear Independence, Subspaces. Linear independence section is critical. Spend extra time on the interactive demos. |  | 50 |  | Ch 00 | Tensors: Indexing, GPU, NumPy | Indexing and slicing. Reproducibility (manual_seed). Device-agnostic code (cuda/cpu). NumPy <-> tensor conversion. Run all code on your RTX 5070 Ti. | 60
1 | Ch 2 | 2026-05-25 | Monday | GT ILA | Read | GT Ch 2 (sections 6-9) | Basis, Dimension, Rank Theorem | Finish GT Ch 2: Basis and Dimension, Bases as Coordinate Systems, The Rank Theorem. Rank Theorem ties everything together. Do all exercises. |  | 50 |  | Ch 00 | BUFFER: Ch 00 Review | Re-do tensor operations from memory without looking. Create a cheat sheet of the 10 most-used tensor ops. If comfortable, start reading Ch 01. | 60
1 | Ch 2 | 2026-05-26 | Tuesday | GT ILA | Read | GT Ch 3 (sections 1-3) | Matrix Transformations, 1-1/Onto, Linear Transformations | Start GT Ch 3: Matrix Transformations, One-to-one and Onto, Linear Transformations. Understand what a linear map preserves. |  | 50 |  | Ch 01 | Data Prep & Model Building | Create synthetic linear data. Train/test split. Build nn.Module subclass (LinearRegressionModel). Understand parameters, forward(). Loss fn (L1Loss, MSELoss) and optimizer (SGD). | 60
1 | Ch 2 | 2026-05-27 | Wednesday | GT ILA | Read | GT Ch 3 (sections 4-6) | Matrix Multiplication, Inverses, Invertible Matrix Thm | Finish GT Ch 3: Matrix Multiplication, Matrix Inverses, Invertible Matrix Theorem. The IMT is the single most important theorem connecting all Ch 2 concepts. |  | 90 |  | Ch 01 | Training Loop & Save/Load | THE core loop: forward pass, loss, zero_grad, backward, step. Train 100+ epochs. Plot loss curves. Evaluate with inference_mode(). Save/load with state_dict. MEMORIZE this loop. | 60
1 | Ch 2 | 2026-05-28 | Thursday | MML | Read | MML 2.4 (groups) + MML 2.8 (affine) | MML Supplements: Groups + Affine Spaces | Read MML 2.4 opening pages on groups/vector space axioms (20 min). Read MML 2.8 on affine spaces/mappings (30 min). Key takeaway: y = Wx + b is affine, not linear. |  | 60 |  | Ch 01 | BUFFER: Ch 01 Review | Write a complete training loop from scratch, no reference. If you cannot do this cold, repeat until you can. This is the single most important skill. | 60
2 | Ch 2 | 2026-05-29 | Friday | MML | Exercise | MML Ex 2.1-2.3 | MML Exercises: Systems & Matrices | Work through MML exercises 2.1-2.3 on paper. These test concepts you read in GT ILA but with MML notation. Bring wrong answers to Claude. |  | 50 |  | Ch 02 | Binary Classification & Nonlinearity | Make circles dataset. Build model with nn.Linear layers. BCEWithLogitsLoss. Sigmoid for predictions. See why linear model fails on nonlinear data. Add nn.ReLU layers. | 60
2 | Ch 2 | 2026-05-30 | Saturday | MML | Exercise | MML Ex 2.4-2.6 | MML Exercises: Vector Spaces, Independence, Rank | Exercises 2.4-2.6. Focus on rank computation and proving/disproving linear independence. Hardest exercises in the set. |  | 50 |  | Ch 02 | Multiclass & Evaluation | Multi-class with softmax + CrossEntropyLoss. Decision boundaries. Accuracy metric. Classification evaluation: confusion matrix concept. Train/test loop with accuracy tracking. | 60
2 | Ch 2 | 2026-05-31 | Sunday | MML | Exercise | MML Ex 2.7-2.9 | MML Exercises: Linear Mappings & Affine | Finish exercises 2.7-2.9. These cover linear mappings and affine spaces. Write 1-page summary of Ch 2 in your own words. |  | 50 |  | Ch 02 | BUFFER: Ch 02 Review | Build a classifier from scratch on a new toy dataset. Experiment: what happens with too few/many hidden units? Too high/low learning rate? Document findings. | 60
2 | Ch 2 | 2026-06-01 | Monday | Python | Python | 2.2-2.3 | Matrix Multiplication from Scratch | Code matmul with nested loops. Verify against numpy @. Handle dimension mismatch errors. | Start 01_matrix_operations.ipynb | 50 |  | Ch 03 | CNN Intro & FashionMNIST | torchvision.datasets.FashionMNIST. DataLoader with batching. Baseline: flatten + linear model. Understand why CNNs exist (spatial structure, parameter sharing). | 60
2 | Ch 2 | 2026-06-02 | Tuesday | Python | Python | 2.1 | Gaussian Elimination | Input: augmented matrix. Output: row echelon form. Handle zero pivots with row swaps. Test 3x3 and 4x4. | Start 02_gaussian_elimination.ipynb | 50 |  | Ch 03 | TinyVGG: Conv2d & MaxPool2d | Build TinyVGG: Conv2d -> ReLU -> Conv2d -> ReLU -> MaxPool2d -> flatten -> Linear. Understand kernel size, stride, padding. Train on FashionMNIST. | 60
2 | Ch 2 | 2026-06-03 | Wednesday | Python | Python | 2.3-2.6 | Inverse, Rank, Null Space | Implement inverse (Gauss-Jordan), rank (count pivots), null_space, col_space, is_independent. Test A @ inv(A) = I. | Start 03_vector_spaces.ipynb | 90 |  | Ch 03 | Model Comparison & Timing | Compare baseline vs CNN: accuracy, loss, training time. Confusion matrix. Predictions on random samples. CPU vs GPU timing. functorch/torchinfo for model summary. | 60
2 | Ch 2 | 2026-06-04 | Thursday | Python | Python | 2.6 | Change of Basis + Rank-Nullity Capstone | Implement change_of_basis(). Capstone: random 5x3, verify rank + nullity = n_cols over 100 trials. Test edge cases: zero, identity, singular matrices. | 04_change_of_basis.ipynb | 60 |  | Ch 03 | BUFFER: Ch 03 Review | Rebuild TinyVGG from memory. Experiment: change kernel size, add layers, change pooling. What improves accuracy? What hurts it? | 60
3 | Ch 2 | 2026-06-05 | Friday | Python | Python | All Ch 2 | linalg.py Module | Refactor all code into clean linalg.py with docstrings: matmul, gauss_elim, rank, inverse, null_space, col_space, change_basis, is_independent. | linalg.py with docstrings | 50 |  | Ch 04 | ImageFolder & Transforms | Download pizza/steak/sushi data. torchvision.datasets.ImageFolder. Compose transforms (Resize, ToTensor, Normalize). Visualize transformed images. DataLoader setup. | 60
3 | Ch 2 | 2026-06-06 | Saturday | Python | Python | All Ch 2 | Write Tests | pytest tests for linalg.py. Cover: identity, singular, rectangular, zero matrix, known solutions. Minimum 10 test cases. | ch02/tests/test_linalg.py | 50 |  | Ch 04 | Custom Dataset Class & Augmentation | Build custom Dataset subclass (__init__, __len__, __getitem__). Data augmentation (RandomHorizontalFlip, RandomRotation, TrivialAugmentWide). Train TinyVGG on custom data. | 60
3 | Ch 2 | 2026-06-07 | Sunday | Python | Python | All Ch 2 | Notebook Polish | Add markdown + LaTeX to all 4 notebooks. Each tells a story: what, why, how, verify. Someone reading should learn from them. | Polish all notebooks | 50 |  | Ch 04 | BUFFER: Ch 04 Review | Create a custom Dataset for a different image folder. Experiment with augmentation combos. Profile data loading speed with different num_workers. | 60
3 | Ch 2 | 2026-06-08 | Monday | Review | Review | All Ch 2 | Self-Test (No Notes) | Without notes: define vector space, basis, rank, null space, independence, affine space. If any is fuzzy, re-read. |  | 50 |  | Ch 05 | Scripts: data_setup, model, engine, train | Convert notebook to .py scripts: data_setup.py (DataLoaders), model_builder.py (TinyVGG), engine.py (train/test step), train.py (entry point), utils.py (save model). Run training from CLI. | 60
3 | Ch 2 | 2026-06-09 | Tuesday | Review | Review | All Ch 2 | ch02/README.md | Write README: concepts, implementations, ML connections (embeddings = vector spaces, rank = information, Wx+b = affine). | ch02/README.md | 50 |  | Ch 05 | BUFFER: Ch 05 Review | Modularize one of YOUR earlier notebooks into scripts. Verify it trains identically. This is professional practice you already know from Schwab; should be fast. | 60
3 | Ch 2 | 2026-06-10 | Wednesday | Python | Python | All Ch 2 | Visualization Notebook | Visual demos: 2D/3D vector ops, span visualization, rank-deficient matrices. matplotlib plots. | Optional: 05_visualizations.ipynb | 90 |  | Ch 06 | Pretrained Models & Feature Extraction | torchvision.models (EfficientNet_B0). Freeze base layers. Replace classifier head. Feature extraction: only train new head. Compare vs TinyVGG from scratch. | 60
3 | Ch 2 | 2026-06-11 | Thursday | Review | Review | All Ch 2 | Final Commit | Run all tests. All notebooks execute clean. Update top-level README. | git push Ch 2. Tag: v0.1-linear-algebra | 60 |  | Ch 06 | Fine-Tuning & Comparison | Unfreeze some/all layers for fine-tuning. Learning rate scheduling. Compare: from-scratch vs feature-extract vs fine-tune. Plot results. Predict on custom images. | 60
4 | Ch 3 | 2026-06-12 | Friday | GT ILA | Read | GT Ch 6: Dot Products & Orthogonality | Norms & Inner Products | Read GT ILA Ch 6 section 1: Dot Products and Orthogonality. Interactive demos for geometric meaning. Cosine similarity = NLP embedding similarity. | Create ch03/ folder | 50 |  | Ch 06 | BUFFER: Ch 06 Review + DONE | Try a different pretrained model (ResNet, ViT). Summarize all chapters in 1 page. PyTorch fundamentals complete. Full focus shifts to MML. | 60 | Ch 1 | Intro (1.1-1.3) | Read SSW Ch 1.1 Intro: What is Learning. Skim 1.2 When to use ML. Light intro day. | 30
4 | Ch 3 | 2026-06-13 | Saturday | GT ILA | Read | GT Ch 6: Orth Complements + Projection + Orth Sets | Projections & Orthogonality | Read GT ILA Ch 6 sections 2-4: Orthogonal Complements, Orthogonal Projection, Orthogonal Sets. Projection is the most important concept. Gram-Schmidt. |  | 50 | [5 empty] | Ch 1 | Intro (1.4) | Read SSW Ch 1.4 Learning Types. Take notes on supervised vs unsupervised framing. | 30
4 | Ch 3 | 2026-06-14 | Sunday | GT ILA + MML | Read | GT Ch 6: Least Squares + MML 3.1-3.4 gaps | Least Squares + MML Review | Finish GT Ch 6: Least Squares. Skim MML 3.1-3.4 for any notation or concepts GT missed (inner product spaces beyond R^n). Light day. |  | 50 | [5 empty] | Ch 1 | Notation review | Read SSW Notation section. Compare to MML notation. Note differences. | 30
4 | Ch 3 | 2026-06-15 | Monday | Python | Python | 3.1-3.3 | Norms, Angles, Cosine Similarity | Implement dot_product, norm, angle_between, cosine_similarity. Verify angle(v,v)=0, angle(v,-v)=pi. | Start 01_norms_and_inner_products.ipynb | 50 | [5 empty] | Ch 1 | Re-read Ch 1 | Re-read Ch 1 end-to-end. Make sure framing is solid before Ch 2 (PAC). | 45
4 | Ch 3 | 2026-06-16 | Tuesday | Python | Python | 3.4 | Projection & Gram-Schmidt | Implement project_onto_subspace and gram_schmidt. Verify: residual orthogonal, output orthonormal. | Start 02_projections_and_gram_schmidt.ipynb | 50 | [5 empty] | Ch 1 | Wrap Ch 1 | Summary notes on Ch 1 (1 page max). What does Shalev-Shwartz mean by "learning"? | 30
4 | Ch 3 | 2026-06-17 | Wednesday | Python | Python | 3.1-3.4 | Capstone + Module | Capstone: 3 random vectors in R5, Gram-Schmidt, verify pairwise dots ~0. Extract geometry.py. Tests. | geometry.py + tests | 90 | [5 empty] | Ch 2 | A Gentle Start (start) | Start SSW Ch 2.1 A Formal Model: Statistical Learning Framework. PAC intuition. | 45
4 | Ch 3 | 2026-06-18 | Thursday | Review | Review | 3.1-3.4 | Ch 3 README & Commit | ch03/README.md. Final commit. | git push Ch 3. Tag: v0.2-analytic-geometry | 60 | [5 empty] | Ch 2 | Ch 2 PAC intuition | Continue SSW Ch 2.1-2.2. Realize how PAC bounds the gap between empirical and true risk. | 45
5 | Ch 4 | 2026-06-19 | Friday | GT ILA | Read | GT Ch 4 (all 3 sections) | Determinants | Read all of GT ILA Ch 4: Definition, Cofactor Expansions, Determinants and Volumes. det=0 means singular. Volume interpretation. | Create ch04/ folder | 50 | [5 empty] | Ch 2 | 2.2 Empirical Risk | Read SSW 2.2 Empirical Risk Minimization. Concept of ERM rule. | 45
5 | Ch 4 | 2026-06-20 | Saturday | GT ILA | Read | GT Ch 4 (finish) + GT Ch 5 start | Determinants Exercises + Eigenvalues Intro | Finish GT Ch 4 exercises. Start GT Ch 5: Eigenvalues and Eigenvectors, Characteristic Polynomial. Core definition: Av = lambda*v. |  | 50 | [5 empty] | Ch 2 | 2.3 ERM with bias | Read SSW 2.3 ERM with Inductive Bias. Why we restrict hypothesis class. | 45
5 | Ch 4 | 2026-06-21 | Sunday | GT ILA | Read | GT Ch 5 (sections 3-6) | Similarity, Diagonalization, Complex Eigen | Finish GT Ch 5: Similarity, Diagonalization, Complex Eigenvalues, Stochastic Matrices. A = PDP^-1 and what it means. |  | 50 | [5 empty] | Ch 2 | 2.3 cont | Continue 2.3. Finite hypothesis class theorem. First real PAC bound. | 45
5 | Ch 4 | 2026-06-22 | Monday | MML | Read | MML 4.4 | SVD (NOT in GT ILA) | Read MML 4.4 carefully. A = U Sigma V^T. Rotate-scale-rotate. This is the most important decomposition in ML and GT ILA does not cover it. |  | 50 | [5 empty] | Ch 2 | Exercises 2.1-2.2 | Try SSW exercises 2.1, 2.2. Bring stuck points to Claude. | 60
5 | Ch 4 | 2026-06-23 | Tuesday | MML | Read | MML 4.5 | Matrix Approximation & PCA (NOT in GT ILA) | Read MML 4.5. Low-rank approx via SVD. Eckart-Young theorem. PCA = project onto top-k singular vectors. |  | 50 | [5 empty] | Ch 2 | Exercises 2.3 | SSW exercise 2.3. Verify ERM bound holds for your toy hypothesis class. | 60
5 | Ch 4 | 2026-06-24 | Wednesday | MML | Exercise | MML Ex 4.1-4.6 | Eigen & SVD Exercises | MML exercises 4.1-4.6. Compute SVD of 2x3 matrix by hand. Find eigenvalues of 3+ matrices. These are hard. |  | 90 | [5 empty] | Ch 2 | Wrap Ch 2 | Summary notes on Ch 2. Why is ERM + finite class = learnable? 1-page write-up. | 45
5 | Ch 4 | 2026-06-25 | Thursday | Review | Exercise | 4.1-4.5 | Remaining Exercises + Summary | Finish exercises. Draw flow: determinants -> eigenvalues -> SVD -> PCA. |  | 60 | [5 empty] | Ch 3 | 3.1 PAC start | Start SSW Ch 3.1 PAC Learning. Formal definition. Read slowly. | 45
6 | Ch 4 | 2026-06-26 | Friday | Python | Python | 4.2 | Power Iteration | Implement power iteration for dominant eigenvector. Observe convergence. Compare with numpy.linalg.eig. | Start 01_eigendecomposition.ipynb | 50 | [5 empty] | Ch 3 | 3.1 cont | Continue 3.1. PAC learnability definition. epsilon, delta meaning. | 45
6 | Ch 4 | 2026-06-27 | Saturday | Python | Python | 4.4 | SVD from Scratch | SVD via: form A^T A, eigendecompose, construct U/Sigma/V^T. Verify A = U @ Sigma @ V^T vs numpy. | Start 02_svd.ipynb | 50 | [5 empty] | Ch 3 | 3.2 A more general framework | Read SSW 3.2. Agnostic PAC learning (no realizable assumption). | 45
6 | Ch 4 | 2026-06-28 | Sunday | Python | Python | 4.5 | PCA from Scratch | Center data, covariance matrix, eigendecompose, project top-k. numpy arrays only. | Start 03_pca.ipynb | 50 | [5 empty] | Ch 3 | 3.2 cont | Continue 3.2. Uniform convergence intuition. | 45
6 | Ch 4 | 2026-06-29 | Monday | Python | Python | 4.5 | PCA Capstone: Iris | Load Iris. YOUR PCA: 4D to 2D. Plot by species. Compare vs sklearn PCA. Diff < 1e-10. | Complete 03_pca.ipynb | 50 | [5 empty] | Ch 3 | 3.3 Learning via UC | Read SSW 3.3 Learning via Uniform Convergence. Connect to ERM. | 45
6 | Ch 4 | 2026-06-30 | Tuesday | Python | Python | 4.4 | Image Compression with SVD | Grayscale image. SVD reconstruct k=5,20,50,100. Side-by-side. Quality vs compression. | 04_image_compression.ipynb | 50 | [5 empty] | Ch 3 | Exercises 3.1-3.2 | SSW exercises 3.1, 3.2. Pen and paper. | 60
6 | Ch 4 | 2026-07-01 | Wednesday | Python | Python | 4.1-4.5 | Module + Tests + Polish | Extract decompositions.py. Write tests. Polish all notebooks with markdown + LaTeX. | decompositions.py + tests | 90 | [5 empty] | Ch 3 | Exercises 3.3 | SSW exercise 3.3 + remaining. Focus on PAC bound derivations. | 60
6 | Ch 4 | 2026-07-02 | Thursday | Review | Review | 4.1-4.5 | Ch 4 README & Commit | ch04/README.md with PCA scatter plot. Final commit. | git push Ch 4. Tag: v0.3-decompositions | 60 | [5 empty] | Ch 3 | Wrap Ch 3 | Summary: PAC vs agnostic PAC vs uniform convergence. 1-page diagram. | 45
7 | Ch 5 | 2026-07-03 | Friday | MML | Read | 5.1 | Univariate Differentiation Review | Read 5.1. Quick review: derivative, product/chain rule. Move fast if comfortable. | Create ch05/ folder | 50 | [5 empty] | Ch 4 | 4.1 Uniform Convergence (skim) | Skim SSW 4.1 Uniform Convergence is Sufficient. Get high-level idea only. | 30
7 | Ch 5 | 2026-07-04 | Saturday | MML | Read | 5.2 | Partial Derivatives & Gradients | Read 5.2. THE most important section for deep learning. Gradient = steepest ascent. Work through ALL examples. |  | 50 | [5 empty] | Ch 4 | 4.2 Finite class is APAC | Read SSW 4.2 Finite Classes are Agnostic PAC Learnable. The big theorem. | 45
7 | Ch 5 | 2026-07-05 | Sunday | MML | Read | 5.3 | Jacobian Matrix | Read 5.3. f: R^n -> R^m has Jacobian shape m x n. Each entry is a partial derivative. |  | 50 | [5 empty] | Ch 4 | Hoeffding inequality | Read SSW Appendix B on Hoeffding inequality. Reference for later. Light skim. | 30
7 | Ch 5 | 2026-07-06 | Monday | MML | Read | 5.4 | Gradients of Matrices | Read 5.4. Matrix calculus: derivatives of trace, det, matrix products. Appears in every ML paper. |  | 50 | [5 empty] | Ch 4 | Wrap Ch 4 | Summary: Why uniform convergence => learnability. Save proof details for ML 391L. | 30
7 | Ch 5 | 2026-07-07 | Tuesday | MML | Read | 5.5, 5.6 | Chain Rule = Backpropagation | Read 5.5-5.6. Composing Jacobians through a computational graph IS backpropagation. Non-negotiable. |  | 50 | [5 empty] | Ch 5 | 5.1 Bias-Complexity | Start SSW Ch 5.1 The No-Free-Lunch Theorem. Read carefully. | 45
7 | Ch 5 | 2026-07-08 | Wednesday | MML | Exercise | 5.1-5.6 | Gradient & Chain Rule Exercises | All chapter exercises. Priority: chain rule on multivariate compositions. Jacobians by hand. |  | 90 | [5 empty] | Ch 5 | 5.1 NFL cont | Finish NFL theorem reading. Implication for hypothesis class choice. | 45
7 | Ch 5 | 2026-07-09 | Thursday | MML | Exercise | 5.5 | Backprop on Paper | Draw 2-layer NN. Forward pass as composition. Chain rule for dL/dW at each layer. PEN AND PAPER. |  | 60 | [5 empty] | Ch 5 | 5.2 Error Decomposition | Read SSW 5.2 Error Decomposition: bias + variance + irreducible. | 45
8 | Ch 5 | 2026-07-10 | Friday | Python | Python | 5.1-5.2 | Numerical Gradients | Finite differences: f'(x) ~ (f(x+h)-f(x-h))/2h. Test on sin, exp, polynomials. | Start 01_numerical_gradients.ipynb | 50 | [5 empty] | Ch 5 | 5.2 cont | Continue 5.2. Approximation error vs estimation error tradeoff. | 45
8 | Ch 5 | 2026-07-11 | Saturday | Python | Python | 5.2-5.3 | Multivariate Gradient & Jacobian | gradient(f, x) for f: R^n -> R. jacobian(f, x) for f: R^n -> R^m. Finite differences. Verify. | Continue 01_numerical_gradients.ipynb | 50 | [5 empty] | Ch 5 | Connect to MML Ch 5 | Connect SSW Ch 5 ideas to MML Ch 5 (vector calculus). Optimization affects estimation error. | 30
8 | Ch 5 | 2026-07-12 | Sunday | Python | Python | 5.5 | Backprop Gradient Verification | 2-layer NN: h=relu(X@W1+b1), y=h@W2+b2, L=MSE. Compute dL/dW analytically. Compare vs PyTorch autograd. | Start 02_backprop_by_hand.ipynb | 50 | [5 empty] | Ch 5 | Exercises 5.1 | SSW exercise 5.1. Bias-complexity tradeoff problem. | 60
8 | Ch 5 | 2026-07-13 | Monday | Python | Python | 5.5 | Backprop Debug & Polish | If gradients match: add complexity. If not: trace chain rule step by step until match. | Complete 02_backprop_by_hand.ipynb | 50 | [5 empty] | Ch 5 | Exercises 5.2 | SSW exercise 5.2 if time permits. Otherwise wrap Ch 5. | 45
8 | Ch 5 | 2026-07-14 | Tuesday | Python | Python | 5.2 | Gradient Visualization | Gradient vector fields for 2D functions. Overlay arrows on loss surface contour plots. | 03_gradient_visualization.ipynb | 50 | [5 empty] | Ch 5 | Wrap Ch 5 | Summary: NFL + bias-complexity. Why no universal learner. 1-page write-up. | 45
8 | Ch 5 | 2026-07-15 | Wednesday | Python | Python | 5.1-5.6 | Module + Tests + Polish | Extract calculus.py (numerical_gradient, jacobian, gradient_check). Tests. Polish notebooks. | calculus.py + tests | 90 | [5 empty] | Ch 6 | 6.1 VC (skim) | Skim SSW Ch 6.1 Restriction of finite class. Concept only. | 30
8 | Ch 5 | 2026-07-16 | Thursday | Review | Review | 5.1-5.6 | Ch 5 README & Commit | ch05/README.md with backprop diagram. | git push Ch 5. Tag: v0.4-vector-calculus | 60 | [5 empty] | Ch 6 | 6.2 VC dimension | Read SSW 6.2 VC Dimension definition. Examples on lines, intervals. | 45
9 | Ch 6 | 2026-07-17 | Friday | MML | Read | 6.1, 6.2 | Probability Spaces + Distributions | Read MML 6.1 (sample space, events, axioms, conditional probability, independence) AND 6.2 (Bernoulli, Binomial, Gaussian, PDF/PMF/CDF) in one day. Focus on Gaussian. |  | 70 | [5 empty] | Ch 6 | 6.2 VC cont | Continue SSW 6.2 VC examples: rectangles, halfspaces. Pen + paper. | 30
9 | Ch 6 | 2026-07-18 | Saturday | MML | Read | 6.3, 6.4 | Bayes Theorem + Multivariate Gaussian | Read MML 6.3 (Bayes: prior, likelihood, posterior, evidence) AND 6.4 (Multivariate Gaussian, mean vector, covariance PSD) together. |  | 70 | [5 empty] | Ch 6 | 6.3 VC Theorem (skim) | Skim SSW 6.3 The Fundamental Theorem of Statistical Learning. Statement only. | 30
9 | Ch 6 | 2026-07-19 | Sunday | MML | Read | 6.5, 6.6 | MLE & MAP | Read MML 6.5-6.6. Derive Gaussian MLE by hand. MSE loss = Gaussian MLE. MAP = MLE + prior = regularization. Most important section for ML 391L. |  | 70 | [5 empty] | Ch 6 | Wrap Ch 6 light | Summary of VC dimension intuition. Save proofs for ML 391L. | 30
9 | Ch 6 | 2026-07-20 | Monday | MML | Exercise | 6.1-6.6 | Probability Exercises Compressed | Pick 4 highest-value MML exercises: one on Bayes, one on Gaussian MLE derivation, one on Bernoulli MLE, one on multivariate Gaussian. Skip the rest. |  | 75 | [5 empty] | Ch 6 | Connect VC to MLE | Note connection: VC bounds generalization, MLE chooses within hypothesis class. | 20
9 | Ch 6 | 2026-07-21 | Tuesday | Python | Python | 6.2-6.5 | Gaussian + Bayesian Posterior | Implement Gaussian class (pdf, log_pdf, sample, fit_mle, no scipy). Then Bayesian posterior with Gaussian prior + likelihood (conjugate). Plot prior/likelihood/posterior. | Start 01_gaussian.ipynb + 02_bayesian.ipynb | 80 | [5 empty] | Review | Review SSW Ch 1-6 | Re-read your own 1-page summaries of SSW Ch 1-6. Strengths/gaps. | 30
9 | Ch 6 | 2026-07-22 | Wednesday | Python | Python | 6.6 | Logistic Regression MLE + MAP | Logistic regression via gradient ascent on log-likelihood. 2D toy data. Add Gaussian prior on weights to get MAP = L2 regularized. Compare boundaries. | Start 03_logistic_regression.ipynb | 80 | [5 empty] | Review | SSW glossary | Make a glossary of SSW terms: PAC, APAC, ERM, VC dim, UC, NFL, realizable, agnostic. | 30
9 | Ch 6 | 2026-07-23 | Thursday | Python+Review | Both | 6.1-6.6 | Module + README + Commit | Extract probability.py with key classes. Skip writing exhaustive tests (just smoke tests). Write README connecting: cross-entropy = Bernoulli MLE, MSE = Gaussian MLE, L2 = Gaussian prior. Commit. | probability.py + ch06/README.md + git push Ch 6. Tag: v0.5-probability | 75 | [5 empty] | Review | Wrap SSW | Quick self-test: define each glossary term cold. Re-read sections that are fuzzy. | 30
10 | Ch 7 | 2026-07-24 | Friday | MML | Read | 7.1, 7.2 | Optimization Framework + GD | Read MML 7.1 (optimization framework: objective, constraints) AND 7.2 (vanilla gradient descent, learning rate, convergence) together. Too big = diverge, too small = stuck. |  | 70 | [5 empty] | Review | SSW summary doc | Compile all SSW summaries into one doc. Save for ML 391L reference. | 45
10 | Ch 7 | 2026-07-25 | Saturday | MML | Read | 7.3 | Convexity + Lagrange | Read MML 7.3 in full: convex sets/functions, convexity guarantees global min, Lagrange multipliers, KKT overview. MSE convex, NN not. |  | 70 | [5 empty] | Review | Plan ML 391L prep | Plan next phase: SSW Ch 7+ during Fall semester, deeper review before Spring 2027. | 30
10 | Ch 7 | 2026-07-26 | Sunday | MML | Read | 7.4 | SGD + Momentum + Adam | Read MML 7.4 + skim supplementary. Mini-batch SGD, momentum, Adam. SGD noise = implicit regularization. |  | 70 | [5 empty] | Review | Cross-link SSW + MML | Map: SSW concepts <-> MML chapters. E.g., SSW Ch 2 ERM <-> MML Ch 7 optimization. | 45
10 | Ch 7 | 2026-07-27 | Monday | MML | Exercise | 7.1-7.4 | GD by Hand + Convexity | 5 iterations of GD on f(x)=x^2+2x+1 with lr=0.1, 0.5, 1.5 by hand. Observe convergence/divergence. Prove one convexity statement. |  | 75 | [5 empty] | Buffer | Catch-up day | Use this day to catch up on anything you missed in SSW Ch 1-6. | 45
10 | Ch 7 | 2026-07-28 | Tuesday | Python | Python | 7.2, 7.4 | Vanilla GD + SGD | GD for f: R^n -> R. Track loss. Test on quadratic and Rosenbrock. Then SGD with mini-batches for linear regression. Compare convergence. | Start 01_gradient_descent.ipynb | 80 | [5 empty] | Buffer | Catch-up day | Continue catch-up or get ahead on SSW Ch 7 (Linear Predictors) if comfortable. | 45
10 | Ch 7 | 2026-07-29 | Wednesday | Python | Python | 7.4 | Momentum + Adam | SGD+momentum and Adam (m/v accumulators, bias correction). Compare all 4 optimizers (GD, SGD, Momentum, Adam) on logistic regression. Loss curves. | Continue 01_gradient_descent.ipynb + 02_optimizer_comparison.ipynb | 80 | [5 empty] | Done | SSW phase 1 done | SSW phase 1 (foundations) complete. Plan: continue SSW during Fall semester light reading. | 30
10 | Ch 7 | 2026-07-30 | Thursday | Python+Review | Both | 7.1-7.4 | Module + README + FINAL Commit | Extract optimizers.py (GD, SGD, Momentum, Adam classes). Smoke tests. README with optimizer comparison chart. Final commit. DONE with MML prep. | optimizers.py + ch07/README.md + git push Ch 7. Tag: v0.6-optimization. MML COMPLETE. | 80 | [5 empty] | Done | Plan finalized | MML + SSW phase 1 both done. 4 weeks buffer before Fall classes start Aug 25. Rest. | 0

## GitHub Milestones
Week | Tag | What Gets Pushed | Notebooks | Module | Tests | README | Commit Msg
Wk 1 |  | Repo init: README, .gitignore, requirements.txt, ch02/ | 0 |  |  | Top-level | feat: init repo
Wk 3 | v0.1-linear-algebra | ch02/: 4-5 notebooks, linalg.py, tests, README | 4-5 | linalg.py | test_linalg.py | ch02/README | feat: ch02 linear algebra from scratch
Wk 3 | pytorch-complete | PyTorch Ch 00-06 done (learnpytorch.io). Tensor ops, training loops, CNNs, custom data, transfer learning. | 0 |  |  |  | milestone: pytorch fundamentals complete
Wk 4 | v0.2-analytic-geometry | ch03/: 2 notebooks, geometry.py, tests, README. SSW Ch 1 notes. | 2 | geometry.py | test_geometry.py | ch03/README | feat: ch03 projections + Gram-Schmidt
Wk 6 | v0.3-decompositions | ch04/: 4 notebooks (incl image compression), decompositions.py. SSW Ch 2 notes. | 4 | decompositions.py | test_decomp.py | ch04/README | feat: ch04 eigen, SVD, PCA
Wk 8 | v0.4-vector-calculus | ch05/: 3 notebooks, calculus.py, tests, README. SSW Ch 3-5 notes. | 3 | calculus.py | test_calculus.py | ch05/README | feat: ch05 gradients + backprop
Wk 9 | v0.5-probability | ch06/: 3 notebooks, probability.py, smoke tests, README. SSW Ch 6 notes. (compressed) | 3 | probability.py | smoke tests | ch06/README | feat: ch06 Gaussian, Bayes, MLE (compressed)
Wk 10 | v0.6-optimization | ch07/: 2 notebooks, optimizers.py, smoke tests, README. SSW phase 1 summary. (compressed) | 2 | optimizers.py | smoke tests | ch07/README | feat: ch07 GD, SGD, Adam (compressed). MML PHASE 1 COMPLETE.
Wk 10 | v0.7-ssw-phase1 | docs/SSW_summary.md: condensed notes on SSW Ch 1-6. Glossary. Cross-link to MML. | 0 |  |  | docs/SSW_summary.md | feat: SSW phase 1 (foundations) complete

## Progress Tracker
Chapter | Weeks | GT ILA Done | MML Read | Exercises | Python | Module | Tests | README | Git Tag | SSW Linked Ch | Confidence | Weak Spots | Date Done
Ch 2: Linear Algebra | Wk 1-3 | GT Ch 1-3 | [7 empty] | N/A (no SSW until Wk 4)
Ch 3: Analytic Geometry | Wk 4 | GT Ch 6 | [7 empty] | SSW Ch 1
Ch 4: Decompositions | Wk 5-6 | GT Ch 4-5 | [7 empty] | SSW Ch 2
Ch 5: Vector Calculus | Wk 7-8 | N/A (MML only) | [7 empty] | SSW Ch 3-5
Ch 6: Probability (compressed) | Wk 9 | N/A (MML only) | [7 empty] | SSW Ch 6 (VC, skim)
Ch 7: Optimization (compressed) | Wk 10 | N/A (MML only) | [7 empty] | SSW wrap
PyTorch (learnpytorch.io Ch 00-06) | Wk 1-3 (parallel) | N/A | learnpytorch.io | Code-along | [5 empty] | N/A
SSW Phase 1 (Ch 1-6 foundational) | Wk 4-10 (parallel) | N/A | SSW Ch 1-6 | Selected exercises | N/A | N/A | N/A | docs/SSW_summary.md | v0.7-ssw-phase1